| UNIVERSITY OF NORTHERN IOWA HLC Sub-Committee Criterion One Mission and Integrity ( The organization operates with integrity to ensure the fulfillment of its mission through structures and processes that involve board, administration, faculty, staff, and students. |
| --- |
| Due Date | Task | Who Responsible |
| Nov. 10 | Send e-mail to subcommittee members to arrange meeting date/time. | Co-Chairs |
| Nov. 17-21 | Schedule meeting with subcommittee members | Co-Chairs |
|  | ( Overview of accreditation and review subcommittee charge |  |
|  | ( Review Criterion One and Five Core Components |  |
|  | ( Delegation of Five Core Components |  |
|  | ( Identify who will write our section |  |
|  | ( Establish regular meeting times/notetaker |  |
|  | Assignment: Read information on HLC website | All members |
|  | Read Chapter 3, The Criteria for Accreditation |  |
| Dec. 1-5 | Subcommittee meeting | Co-Chairs |
|  | ( Brainstorm types of evidence for Criterion One; 1a, 1b | All members |
|  | ( Design evaluation form to unify how evidence is collected/recorded |  |
|  | ( Demonstration of SharePoint, HLC website |  |
|  | Assignment: Read previous self-study. |  |
|  | Committee members continue to identify types of evidence. |  |
| Dec. 15-19 | Subcommittee meeting | Co-Chairs |
|  | ( Brainstorm types of evidence for 1c, 1d, 1e | All members |
|  | ( Subcommittee members add evidence to 1a, 1b, 1c |  |
|  | ( Review draft of evidence evaluation form | Co-Chair |
|  | Assignment: Committee members continue identifying types of evidence. | All members |
|  | Gather evidence that pertains to your core component. | Assigned members |
| Dec. 19 - Jan. 9 | Holiday Break Assignment: Continue identifying and gathering evidence. | All members |
|  | Read Bob Appleson materials. Begin checking other criterions, etc. which reference data needed in Criterion One. | All members |
| Jan. 12-16 | Subcommittee meeting | All members |
|  | ( Distribute evidence evaluation form. | Co-Chair |
|  | ( Review identified evidence to date. |  |
|  | ( Finalize evidence into appropriate core components (Master Evidence List). |  |
|  | ( Prepare summary list of other criterion needing same/similar evidence/documents |  |
|  | ( Prepare request for documents to data coordinators. | Co-Chairs |
|  | ( Prepare list of campus individuals we need to interview (via e-mail or in person) and subject. |  |
|  | ( Determine who will make contact with each individual. |  |
|  | Assignment: Send in data request to data coordinators. | Co-Chairs |
|  | ( Schedule meetings with individual we need to interview. | Assigned members |
|  | ( Review last self-study. |  |
|  | Last call for data request. |  |
| Jan. 26-30 | Subcommittee meeting | Co-Chairs |
|  | ( Discuss uniform outline format each group will use in preparing information for writer. | Writer |
|  | ( Share information from contacts with individuals. | Assigned members |
|  | Assignment: |  |
| Feb. 9-13 | Subcommittee meeting | Co-Chairs |
|  | ( Interpret evidence and begin preparing outlines. | All members |
|  | Assignment: Continue interpreting and summarizing strength of evidence. |  |
| Feb. 23-27 | Subcommittee meeting | Co-Chairs |
|  | ( Review members( progress in preparing outlines and discuss any concerns. | All members |
|  | ( Subcommittee continues to interpret evidence and prepares outlines. | Assigned members |
|  | Assignment: Continue to prepare outlines. | Assigned members |
| Mar. 9-13 | Subcommittee submits core component outlines/drafts to subcommittee(s writer. | Assigned members |
| Mar. 16-20 | Spring Break Writer begins drafting document for Criterion One. | Writer |
| Mar. 23-27 | Subcommittee meeting | Co-Chairs |
|  | ( Review progress to draft document. |  |
|  | ( Address concerns/needs, etc. |  |
|  | Assignment: Writer continues to draft Criterion One. | Writer |
| Mar. 30-April 3 | Assignment: Writer submits electronic draft to members for comments. | Writer |
|  | Assignment: Respond with comments on first draft of document. | All members |
| April 6-10 | Subcommittee meeting | Co-Chairs |
|  | ( Review revisions to first draft of written document. | All members |
|  | Assignment: Continue writing document. | Writer |
| April 20-24 | Subcommittee reviews second draft and submits comments/revisions to writer. | All members |
|  | Writer makes revisions and submits revised draft electronically to members for final review. | Writer |
|  | Final call for revisions. | Writer |
| April 27-30 | Writer and Co-Chairs meet to review final draft. | Writer Co-Chairs |
| May 1 | Subcommittee submits draft to HLC Steering Committee. |  |